## Sheet1
Deliverable / Due | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Weekly Team Status Report | 2014-07-13 | 2014-07-20 | 2014-07-27 | 2014-08-03 | 2014-08-10 | 2014-08-17 | 2014-08-24
Weekly Time Sheet | 2014-07-13 | 2014-07-20 | 2014-07-27 | 2014-08-03 | 2014-08-10 | 2014-08-17 | 2014-08-24
Initial Project Plan | 2014-07-13: 2014-07-13
Team Charter | 2014-07-20: 2014-07-20
Draft Requirements Specification | 2014-07-20: 2014-07-20
Draft Design Specification | 2014-08-03: 2014-08-03
Draft Test Plan, Policies, and Procedures | 2014-08-17: 2014-08-17
Unit/Component code components | 2014-08-17: 2014-08-17
Schedule Team Presentation | 2014-08-17: +; 2014-08-24: 2014-08-20
Team Presentations (Monday week 8) | [7 empty] | 2014-08-25
Team Presentations (Tuesday week 8) | [7 empty] | 2014-08-26
Power Point Presentation | [7 empty] | 2014-08-28
Completed Application | [7 empty] | 2014-08-28
Final Project Plan | [7 empty] | 2014-08-28
Final Requirements Specification | [7 empty] | 2014-08-28
Final Design Specification | [7 empty] | 2014-08-28
Final Test Plan | [7 empty] | 2014-08-28
Final Deployment Plan | [7 empty] | 2014-08-28
Note on G11: Begin scheduling team presentations for Week 8
Note on H11: D99001728: You must schedule your team presentation time by Thursday - Week 7